## CIP EMS Facilities
Table 26A: Capital Fund Facilities Plan for Wake County EMS Facilities (Footnote #23 and Footnote #25)
CID | Station | Department Organization | Reg. | Type | Status | Heery Estimate | Land Cost | New Construction Cost | Land and Construction Cost | Cost Avoidance | Action Date | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018
E1 | EMS1 (Footnote #13 and #17) | County | NW | EHQ | OK | 0 | 0 | 0 | 0 | 0 | 2005 | 0 | 713736 | 57464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EMS1 (Footnote #16) | County |  | ES | New |  | 260000 | 627330 | 887330 |  | 2006 | FY 2005: 443665; FY 2006: 443665
E2 | EMS2 | County | NW | ES | OK | 126145 | 0 | 0 | 0 | 126145 | 2004 | 77941 | 31822 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E3 | EMS3 | County | NW | ES | OK | 54903 | 0 | 0 | 0 | 54903 | 2004 | 2344 | 23440 | 29119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E4 | EMS4 | County | SW | ES | OK | 95276 | 0 | 0 | 0 | 95276 | 2004 | 56599 | 26281 | 9839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E5 | EMS5 | County | NE | ES | OK | 117802 | 0 | 0 | 0 | 117802 | 2004 | 74969 | 31894 | 2911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E6 | EMS6 (Footnote #11) | County | SW | ES | OK | 0 | 0 | 0 | 0 | 0 |  | 0 | 48400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E7 | EMS7 | County | NW | ES | OK | 86540 | 0 | 0 | 0 | 86540 | 2004 | 48229 | 31124 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E8 | EMS8 | County | NW | ES | OK | 71785 | 0 | 0 | 0 | 71785 | 2004 | 43966 | 24589 | 2081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E10 | EMS10 | County | NW | ES | OK | 81773 | 0 | 0 | 0 | 81773 | 2004 | 43327 | 30943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E15 | EMS15 (Footnote #6 and #15) | County | NW | EFS | New | 0 | 55200 | 442726.724 | 497926.724 | 0 | 2011 | 0 | 0 | 0 |  | 0 | 0 | 248963.362 | 248963.362 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | Apex EMS | Private-Non-Profit | SW | EHQ | OK | 188173 | 0 | 0 | 0 | 188173 | 2004 | 37503 | 90682 | 18742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N/A | Cary EMS (Footnote #11, #12 and #17) | Private-Non-Profit | SW | EHQ | OK | 252066 | 0 | 0 | 0 | 252066 | 2004 | 102589 | 478563 | 113125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Garner EMS (Footnote #11) | Private-Non-Profit | SW | EHQ | OK | 270064 | 0 | 0 | 0 | 270064 | 2004 | 38789 | 202668 | 16497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Garner EMS (Footnote #14) | Private-Non-Profit |  | EFHQ | New |  | 92000 | 593010 | 685010 |  | 2006 | FY 2005: 342505; FY 2006: 342505
87 | Holly Springs EMS | Municipal | SW | ES | OK | 7137 | 0 | 0 | 0 | 7137 | 2004 | 0 | 0 | 7137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | Knightdale EMS | Private-Non-Profit | NE | EHQ | OK | 227632 | 0 | 0 | 0 | 227632 | 2004 | 45353 | 116616 | 19366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | Rolesville EMS (Footnote #3) | Private-Non-Profit | NW | EHQ | Under Construction | 0 | 0 | 0 | 0 | 0 | 2003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | Six Forks Rescue (Footnote #5) | Private-Non-Profit | NW | EHQ | Alt Use | 460151 | 0 | 0 | 0 | 460151 | 2005 | 37543 | 216670 | 80185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | Wendell EMS (Footnote #11) | Private-Non-Profit | NE | EMSHQ | New | 150873 | 0 | 731149 | 731149 | 0 | 2006 | 32261 | 196853 | 668014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Zebulon EMS | Private-Non-Profit | NE | EMSHQ | New | 149267 | 0 | 731149 | 731149 | 0 | 2008 | 84863 | 35159 | 29245 | 80000 | 651149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tethered Electrical Shoreline Connection Upgrade | [10 empty] | FY 2006: 50000
| ZZZZ | TOTAL (Footnote #18) |  |  |  | 2339587 | 407200 | 3125364.724 | 3532564.724 | 2039447 |  | 726276 | 3085610 | 1847966 | 80000 | 651149 | 0 | 248963.362 | 248963.362 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## CIP Fire Facilities
Table 26B: Capital Plan for Wake County Fire Facilities (Footnote #23 and Footnote #25)
CID | Station | Department Organization | Reg. | Station Type (Footnote #20) | Status | Heery Estimate | Land Cost (Footnote #21) | New Construction Cost (Footnote #22) | Land and Construction Cost | County Cost Share Amount (Footnote #19) | Adj. Cost Avoidance | Project Completion Date (Footnote #24) | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018
4 | Apex #1 | Municipal | SW | FS | Close | 2824561 | 0 | 0 | 0 |  | 2824561 | 2004 | 4688 | 519407 | 127671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Apex #1 (Footnote #1) | Municipal | SW | FS | New | 0 | 400000 | 1424020 | 1824020 | 386144 | 0 | 2010 | 0 | 0 |  | 0 | 0 | 193072 | 193072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | Apex #2 | Municipal | SW | FS | OK | 1458765 | 0 | 0 |  |  | 1458765 | 2005 | 3515 | 459316 | 90768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | Apex #3 | Municipal | SW | FHQ | OK | 0 | 0 | 0 | 0 |  | 0 | 2005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N/A | Apex #4 (Footnote #1) | Municipal | SW | FS | New | 0 | 120000 | 1424020 | 1544020 | 535286 | 0 | 2006 | 0 | 267643 | 267643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Bayleaf #1 (Footnote #9) | Private-Non-Profit | NW | FHQ | OK | 1645950 | 0 | 0 | 0 |  | 1645950 | 2005 | 193198 | 970958 | 27632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | Bayleaf #2 | Private-Non-Profit | NW | FS | OK | 548886 | 0 | 0 | 0 |  | 548886 | 2005 | 35655 | 43245 | 17192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Bayleaf #3 (Footnote #5) | Private-Non-Profit | NW | FS | Alt Use | 540777 | 0 | 0 | 0 |  | 540777 | 2005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N/A | Bayleaf #4 (Footnote #6) | Private-Non-Profit | NW | FES | New | 0 | 240000 | 1482172.076 | 1722172.076 |  | 0 | 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 861086.038 | 861086.038 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Durham Highway #1 | Private-Non-Profit | NW | FHQ | OK | 538353 | 0 | 0 | 0 |  | 538353 | 2005 | 38795 | 90546 | 2293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Durham Highway #2 | Private-Non-Profit | NW | FS | OK | 0 | 0 | 0 | 0 |  | 0 | 2005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | Eastern Wake #1 | Private-Non-Profit | NE | FHQ | OK | 379360 | 0 | 0 | 0 |  | 379360 | 2005 | 25541 | 16020 | 134978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Eastern Wake #2 | Private-Non-Profit | NE | FS | Close | 1819841 | 0 | 0 | 0 |  | 1819841 | 2005 | 44490 | 504906 | 115780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N/A | Eastern Wake #2 | Private-Non-Profit | NE | FS | New | 1819841 | 150000 | 1424020 | 1574020 |  | 0 | 2010 | 0 | 0 | 0 | 0 | 0 | 787010 | 787010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Fairview #1 | Private-Non-Profit | SW | FHQ | OK | 386971 | 0 | 0 | 0 |  | 386971 | 2005 | 21948 | 36117 | 127852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Fairview #2 | Private-Non-Profit | SW | FS | OK | 1898251 | 0 | 0 | 0 |  | 1898251 | 2005 | 34353 | 538924 | 37127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Falls #1 | Private-Non-Profit | NW | FHQ | Close | 564242 | 0 | 0 | 0 |  | 564242 | 2004 | 8913 | 187940 | 54423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Fuquay-Varina #1 | Municipal | SW | FHQ | OK | 1652087 | 0 | 0 | 0 |  | 1652087 | 2005 | 45677 | 7735 | 459227 | 63926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Fuquay-Varina #2 | Municipal | SW | FS | OK | 3122679 | 0 | 0 | 0 |  | 3122679 | 2005 | 74772 | 35377 | 422315 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | Fuquay-Varina #3 | Municipal | SW | FS | OK | 0 | 0 | 0 | 0 |  | 0 | 2005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N/A | Fuquay-Varina #4 (Footnote #1) | Municipal | SW | FS | New | 0 | 150000 | 1424020 | 1574020 | 1285759 | 0 | 2010 | 0 | 0 | 0 | 0 | 0 | 642879.5 | 642879.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | Garner #1 | Private-Non-Profit | SW | FHQ | Close | 278586 | 0 | 0 | 0 |  | 278586 | 2008 | 0 | 8653 | 127852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | Garner #1 (Footnote #2) | Private-Non-Profit | SW | FEHQ | New | 0 | 308000 | 1985294.85 | 2293294.85 | 440430 | 0 | 2006 | 0 | 188494.5 | 188494.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Garner #2 | Private-Non-Profit | SW | FS | OK | 1632618 | 0 | 0 | 0 |  | 1632618 | 2005 | 27701 | 136720 | 379499 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Garner #3 | Private-Non-Profit | SW | FS | OK | 535032 | 0 | 0 | 0 |  | 535032 | 2005 | 21647 | 52652 | 178036 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N/A | Garner #4 (Footnote #8) | Private-Non-Profit | SW | FS | New | 0 | 0 | 0 | 0 |  | 0 | 2006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Holly Springs #1 | Municipal | SW | FS | OK | 1233014 | 0 | 0 | 0 |  | 1233014 | 2005 | 32158 | 98895 | 269535 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | Holly Springs #2 | Municipal | SW | FHQ | Close | 351350 | 0 | 0 | 0 |  | 351350 | 2004 | 0 | 88214 | 69056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | Holly Springs #2 (Footnote #1 & #3) | Municipal | SW | FHQ | New | 0 | 0 | 0 | 0 |  | 0 | 2005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Hopkins #1 | Private-Non-Profit | NE | FHQ | OK | 1875628 | 0 | 0 | 0 |  | 1875628 | 2006 | 54677 | 78013 | 91083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N/A | Knightdale #1 (Footnote #1) | Municipal | NE | FHQ | New | 0 | 400000 | 2252154 | 2652154 | 1108813 | 0 | 2006 | 0 | 1326077 | 554406.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N/A | Knightdale #2 (Footnote #1) | Municipal | NE | FS | New | 0 | 120000 | 1424020 | 1544020 | 919126 | 0 | 2006 | 0 | 459563 | 459563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Morrisville #1 | Municipal | SW | FHQ | Close | 467696 | 0 | 0 | 0 |  | 467696 | 2004 | 0 | 127519 | 67066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Morrisville #1 (Footnote #7) | Municipal | SW | FHQ | New | 0 | 0 | 0 | 0 |  | 0 | 2006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | Morrisville #2 | Municipal | SW | FS | OK | 425210 | 0 | 0 | 0 |  | 425210 | 2005 | 11152 | 19747 | 2310 | 127852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Morrisville #3 (Footnote #17) | Municipal | SW | FS | Close | 446634 | 0 | 0 | 0 |  | 446634 | 2005 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Rolesville #1 | Private-Non-Profit | NW | FHQ | OK | 1765733 | 0 | 0 | 0 |  | 1765733 | 2005 | 90859 | 37340 | 221279 | 161946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Stony Hill #1 | Private-Non-Profit | NW | FHQ | Close | 0 | 0 | 0 | 0 |  | 0 | 2004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Stony Hill #1 (Footnotes #3 & $4) | Private-Non-Profit | NW | FEHQ | New | 0 | 0 | 0 | 0 |  | 0 | 2004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | Stony Hill #2 | Private-Non-Profit | NW | FS | OK | 1087982 | 0 | 0 | 0 |  | 1087982 | 2005 | 41821 | 57108 | 5995 | 85235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Swift Creek #1 | Private-Non-Profit | SW | FHQ | OK | 502286 | 0 | 0 | 0 |  | 502286 | 2004 | 73751 | 97512 | 2247 | 76711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Wake Forest #1 | Private-Non-Profit | NW | FHQ | OK | 1694482 | 0 | 0 | 0 |  | 1694482 | 2005 | 29223 | 42565 | 432037 | 234395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | Wake Forest #2 | Private-Non-Profit | NW | FS | OK | 237639 | 0 | 0 | 0 |  | 237639 | 2005 | 10086 | 2983 | 15626 | 85235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N/A | Wake Forest #3 (Footnote #2) | Private-Non-Profit | NW | FS | New | 0 | 150000 | 1424020 | 1574020 | 419753 | 0 | 2007 | 0 | 0 | 209876.5 | 209876.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N/A | Wake Forest #4 (Footnote #2) | Private-Non-Profit | NW | FS | New | 0 | 120000 | 1424020 | 1544020 | 1112821 | 0 | 2009 | 0 | 0 | 0 | 0 | 556410.5 | 556410.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Wake-New Hope #1 (Footnote #17) | Private-Non-Profit | NE | FHQ | Close | 1040714.0507 | 0 | 0 | 0 |  | 1040714.0507 | 2004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Wake-New Hope #2 | Private-Non-Profit | NE | FS | OK | 1086955.2864 | 0 | 0 | 0 |  | 1086955.2864 | 2005 | 31203 | 40650 | 224225 | 213087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Wendell #1 | Private-Non-Profit | NE | FHQ | OK | 238081.7764 | 0 | 0 | 0 |  | 238081.7764 | 2005 | 16479 | 17472 | 85438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Wendell #2 | Private-Non-Profit | NE | FS | OK | 443802.7851 | 0 | 0 | 0 |  | 443802.7851 | 2005 | 24434 | 42592 | 7435 | 150581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Western Wake #1 | Private-Non-Profit | SW | FHQ | Close | 474810 | 0 | 0 | 0 |  | 474810 | 2004 | 77367 | 29743 | 4147 | 127852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Western Wake #2 | Private-Non-Profit | SW | FS | Close | 354860 | 0 | 0 | 0 |  | 354860 | 2004 | 33214 | 95696 | 10457 | 34094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Zebulon #1 | Municipal | NE | FHQ | OK | 448880 | 0 | 0 | 0 |  | 448880 | 2005 | 40128 | 15860 | 53860 | 127852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dormitory Improvements (Design and Bidding) | N/A |  | N/A | N/A | [7 empty] | FY 2005: 335000
| Functional Programmatic Renovations (Footnote #10) | [11 empty] | FY 2005: 100000; FY 2008: 2535761; FY 2012: 2535761; FY 2013: 2535761; FY 2014: 2535761
| Aestethic Programmatic Renovations | [11 empty] | FY 2008: 253392; FY 2012: 253392; FY 2013: 253392; FY 2014: 253392
| ZZZZ | TOTAL (Footnote #18) |  |  |  | 35822557.8987 | 2158000 | 15687760.926 | 17845760.926 |  | 34002716.8987 |  | 1147445 | 7177202.5 | 5544424.5 | 1698642.5 | 3345563.5 | 2179372 | 2484047.538 | 861086.038 | 2789153 | 2789153 | 2789153 | 0 | 0 | 0 | 0

## Footnotes for CIP
Footnotes for Tables 26A and 26B
Footnotes for CIP EMS and Fire Facilities | This station is a municipal fire station. Construction cost shown is the total anticipated construction cost for the prototype fire station. Construction costs are recommended to be shared between the County and the municipality. County cost share shown in column titled "County Cost Share Amount." County costs are spread over two years.
#2 | This station is operated by a private non-profit corporation (PNP) that serves both municipal and unincorporated areas. The construction costs are recommended to be shared between the County and the municipality. County cost share shown in column titled "County Cost Share Amount." County costs are spread over two years.
#3 | This station is already under construction and budgeted. No additional construction costs are shown.
#4 | This station is a joint fire and EMS station. The costs are shared between the two disciplines.
#5 | This station is recommended to be vacated for fire service use but maintained for EMS use.
#6 | This is a joint Fire/EMS station. Cost allocation for Fire is shown under the Fire Stations, and cost allocation for EMS stations is shown under EMS. Costs split 77% fire and 23% EMS.
#7 | This is a municipal fire station, This station is constructed for relocation as a result of railroad line expansion and not as a result of service needs. No costs are shown.
#8 | Funds for this station are already budgeted in Wake County's CIP. The total project cost estiamtes in Wake County's CIP is $1,702,120. Of that amount, $275,00 is funded prior to FY 04, and $1,427,120 is funded in FY 04.
#9 | Given recommendation to close Station #3, funds are allocated for additional space at Bay Leaf #1. Prior to spending funds to add additional space to Station #1, Wake County should thoroughly analyze all options to meet space needs of Bay Leaf fire department.
#10 | These funds are to conduct update/analysis of functional programmatic renovation requirements.
#11 | $48,400 budgeted in FY 2005 to accommodate relocation of an EMS unit to a fire station.
#12 | $193,600 budgeted in FY 2005 to accommodate relocation of an EMS unit to a fire station.
#13 | EMS Scenario recommends closing current EMS Station 1 and opening one new station and relocating two additional units. $242,000 budgeted in FY 2005 for two relocations.
#14 | This is an EMS unit relocation to the relocated Garner Fire Station #1. Costs split 77% fire and 23% EMS.
#15 | Costs shown are for a joint Fire/EMS station. Consideration may be given to relocating EMS unit at the northern Wake hospital.
#16 | This is a new station to accommodate units relocated due to closing of current EMS Station 1.
#17 | Given recommendation to relocate an EMS unit to a fire station not recommended for future fire use, HEERY costs are allocated to the appropriate EMS agency.
#18 | Total cost does not reflect sources of funds. Funding sources include but are not limited to fire tax revenues, general fund revenues, departmental fund balances, corporate donations, etc.
#19 | County cost shown is calculated based on the "North Shore" formula.
#20 | Station Types: EFHQ=EMS Portion of Fire/EMS headquarters co-location prototype. EMSHQ=EMS headquarters station prototype. ES=EMS substation prototype. EFS=EMS portion of EMS/Fire substation co-location prototype. FEHQ=Fire portion of Fire/EMS co-location prototype. FES=Fire portion of fire/EMS prototype substation. FHQ=Fire headquarters prototype. FS=Fire substation prototype.
#21 | Land cost data supplied by Wake County Facilities Design and Construction Department.
#22 | New construction cost data supplied by Wake County Facilities Design and Construction and based on construction of Wake County prototype plans.
#23 | This Capital Improvement Plan is a recommendation of Tri-Data based in part on data provided by Wake County staff. Note: Shaded rows are new stations for private non-proft corporation fire departments.
#24 | Project completion date represents when a particular station is needed based on demand analysis. Given the need to spread new station funding over two year consecutive years, three stations are projected to be needed in FY 05 but are funded in FY 05 and FY 06. Therefore the project completion date for these three stations in the CIP chart is FY 06. The three stations are Garner #1, Knightdale #1 and Knightdale #2.
#25 | All costs shown are in 2004 dollars (January 1, 2004). Project costs for projects implemented after January 1, 2004, will need to have appropriate annual escalation factor(s) applied.

## Assumptions
Type | Total Cost | Acres Needed |  | OK
EFHQ | 593010 | 3 |  | New
EMSHQ | 731149 | 3
ES | 627330 | 1.5 |  | Close
EFS | 442726.724
FEHQ | 1985294.85 | 7.5 |  | Alt Use
FES | 1482172.076 | 4.5 |  | Ren
FHQ | 2252154 | 5.5
FS | 1424020 | 3.5
Region
NE | 54900 |  | Notes to Users:
NW | 63300 |  | User editable assumptions are in yellow boxes.
SE | 33100 |  | Do not attempt to edit any other portion of this sheet.
SW | 57800
Cost Escalation Functions
Starting Year | 2004
Escalation | 0%
FF&E | 0%
Prof. Svcs. | 0%
Reg. Fees | 0%
Contingency | 0%

## Heery Data
Place an 'X' in a blue box to include a task. |  | Heery | Total for Selected |  | Life Safety |  | Bldg. Env. |  | Sys. Reliab. | Total for | Total Left Over for | Emer Prep |  | Life Cycle |  | Code Compl. | Total for | Bunk Room |  |  |  | Veh. Exhaust |  |  |  | Funct. Proto. | ADA Compl. | Aesth. Proto.
CID | Station | Total | Work |  | 1 |  | 2 |  | 3 | FY 04 | FY 05 | 4 |  | 5 |  | 6 | FY05 | 6A |  |  |  | 7 |  |  |  | 8 | 9 | 10
4 | Apex #1 | 2824561 | 93358 | x | 4688 | x | 88670 |  | 22729 | 4688 | 111399 |  |  | 33021 |  | 1193 | 145613 | 373794 | 373794 |  |  | 126005 | 126005 |  |  | 1410804 | 492 | 1666
40 | Apex #2 | 1458765 | 3515 | x |  | x | 3515 |  | 12359 | 3515 | 12359 |  |  | 894 |  |  | 13253 | 446063 | 446063 |  |  | 85235 | 85235 |  |  | 341342 | 5533 | 3399
44 | Apex #3 | 0 | 0 | x |  | x |  |  |  | 0 | [6 empty] | 0
| Apex #4 |  | 0 | [6 empty] | 0 | [6 empty] | 0
25 | Bayleaf #1 | 1645950 | 870317 | x | 13370 | x | 56947 |  | 18041 | 13370 | 74988 | 42617 |  | 28967 |  | 33256 | 179828 | 170958 | 170958 | [5 empty] | x | 800000 | 27632 | 15018 |  |  | 469038
36 | Bayleaf #2 | 548886 | 35655 | x |  | x | 35655 |  | 5398 | 35655 | 5398 |  |  | 24302 |  | 13545 | 43245 | [8 empty] | 366340 | 17192 | 2156
12 | Bayleaf #3 | 540777 | 0 |  | 852 |  | 34986 |  | 7245 | 0 | 43083 | 1705 |  | 79726 |  | 38782 | 163296 |  |  |  |  | 90917 |  |  |  |  | 46621 | 33564
| Bayleaf #4 |  | 0 | [6 empty] | 0 | [6 empty] | 0
16 | Durham Highway #1 | 538353 | 29987 | x | 1279 | x | 28708 |  | 8808 | 29987 | 8808 | 142 |  | 32497 |  | 57907 | 99354 | [8 empty] | 266776 | 2293 | 1794
17 | Durham Highway #2 | 0 | 0 | x |  | x |  |  |  | 0 | [6 empty] | 0
38 | Eastern Wake #1 | 379360 | 2101 | x | 426 | x | 1675 |  | 23440 | 2101 | 23440 |  |  | 5677 |  | 399 | 29516 | 9944 | 9944 |  |  | 127852 | 127852 |  |  | 6677 | 7126 | 3291
13 | Eastern Wake #2 | 1819841 | 32912 | x | 2273 | x | 30639 |  | 11578 | 2273 | 42217 |  |  | 41511 |  | 24357 | 108085 | 439038 | 439038 |  |  | 107964 | 107964 |  |  | 357935 | 7816 | 97153
| Eastern Wake #3 |  | 0 | [6 empty] | 0 | [6 empty] | 0
20 | Fairview #1 | 386971 | 9163 | x |  | x | 9163 |  | 12785 | 9163 | 12785 |  |  | 7705 |  |  | 20490 | 28412 | 28412 |  |  | 127852 | 127852 |  |  |  |  | 2352
34 | Fairview #2 | 1898251 | 34353 | x | 1705 | x | 32648 |  | 6393 | 34353 | 6393 |  |  | 14388 |  | 5650 | 26431 | 512493 | 512493 |  |  | 34094 | 34094 |  |  | 594914 | 3033 | 79169
21 | Falls #1 | 564242 | 8913 | x | 8913 |  | 39856 |  | 12643 | 8913 | 52499 | 44322 |  | 29406 |  | 23357 | 149584 | 38356 | 38356 |  |  | 45458 | 45458 |  |  |  | 8965 | 18156
33 | Fuquay-Varina #1 | 1652087 | 33602 | x |  | x | 33602 |  | 12075 | 33602 | 12075 |  |  | 3867 |  | 3868 | 19810 | 458342 |  | 458342 |  | 63926 |  | 63926 |  | 467774 | 885 | 19993
[10 empty] | 0 | [6 empty] | 0
[10 empty] | 0 | [6 empty] | 0
7 | Fuquay-Varina #2 | 3122679 | 60140 | x |  | x | 60140 |  | 14632 | 0 | 74772 |  |  | 21974 |  | 13403 | 110149 | 224517 |  | 224517 |  | 191778 | 191778 |  |  | 1921570 | 6020 | 67429
45 | Fuquay-Varina #3 | 0 | 0 | x |  | x |  |  |  | 0 | [6 empty] | 0
41 | Garner #1 | 278586 | 5576 | x |  | x | 5576 |  |  | 0 | 5576 | 1279 |  | 1798 |  |  | 8653 |  |  |  |  | 127852 | 127852
18 | Garner #2 | 1632618 | 27701 | x | 852 | x | 26849 |  | 31111 | 27701 | 31111 |  |  | 1509 |  | 104100 | 136720 | 281071 |  | 281071 |  | 98020 | 98020 |  |  | 483703 | 408 | 30372
8 | Garner #3 | 535032 | 21647 | x | 20151 | x | 1496 |  | 35088 | 21647 | 35088 |  |  | 11589 |  | 5975 | 52652 | 2841 |  | 2841 |  | 170469 | 170469 |  |  |  | 4726
| Garner #4 |  | 0 | [6 empty] | 0 | [6 empty] | 0
14 | Holly Springs #1 | 1233014 | 32158 | x | 1705 | x | 30453 |  | 26565 | 32158 | 26565 | 42617 |  | 14486 |  | 15227 | 98895 | 223977 |  | 223977 |  | 39978 | 39978 |  |  | 344019 | 5580 | 66834
37 | Holly Springs #2 | 351350 | 2557 | x | 2557 |  | 7103 |  | 24434 | 0 | 34094 |  |  | 14246 |  | 39874 | 88214 | 2841 |  | 2841 |  | 65347 | 65347 |  |  |  | 868 | 3584
22 | Hopkins #1 | 1875628 | 54677 | x | 2557 | x | 52120 |  | 14774 | 54677 | 14774 | 1279 |  | 46979 |  | 14981 | 78013 |  |  |  |  | 56823 | 56823 |  |  | 1143611 | 34260 | 303957
| Knightdale #2 |  | 0 | x |  | x |  |  |  | 0 | [6 empty] | 0
23 | Morrisville #1 | 467696 | 18286 | x | 18286 |  | 44092 |  | 21877 | 0 | 84255 | 426 |  | 24001 |  | 18837 | 127519 | 2841 |  | 2841 |  | 45458 | 45458 |  |  | 6556 | 18767 | 6482
42 | Morrisville #2 | 425210 | 11152 | x |  | x | 11152 |  | 4120 | 11152 | 4120 | 1563 |  | 81 |  | 13983 | 19747 |  |  |  |  | 127852 |  | 127852 |  | 96766 | 2310 | 4512
24 | Morrisville #3 | 446634 | 2131 | x | 2131 |  | 23552 |  | 11223 | 25683 | 11223 | 42617 |  | 39094 |  | 13179 | 106113 | 38356 |  | 38356 |  | 22729 | 22729 |  |  | 3963 | 9676 | 36010
15 | Rolesville #1 | 1765733 | 71965 | x | 1705 | x | 70260 |  | 18894 | 71965 | 18894 | 1705 |  | 12265 |  | 23370 | 56234 | 148418 |  | 148418 |  | 161946 |  | 161946 |  | 663319 | 72861 | 133533
26 | Stony Hill #1 | 0 | 0 | x |  | x |  |  |  | 0 | [6 empty] | 0
39 | Stony Hill #2 | 1087982 | 37701 | x | 426 | x | 37275 |  | 4120 | 41821 |  | 42759 |  | 686 |  | 13663 | 57108 |  |  |  |  | 85235 |  | 85235 |  | 706465 | 5995 | 7194
27 | Swift Creek #1 | 502286 | 41362 | x | 4688 | x | 36674 |  | 32389 | 73751 |  |  |  | 62770 |  | 24798 | 87568 | 9944 | 9944 |  |  | 76711 |  | 76711 |  |  | 2247 | 4091
| Swift Creek #2 |  | 0 | x |  | x |  |  |  | 0 | [6 empty] | 0
6 | Wake Forest #1 | 1694482 | 29223 | x | 5114 | x | 24109 |  | 30827 | 29223 | 30827 |  |  | 10464 |  | 1274 | 42565 | 424766 |  | 424766 |  | 234395 |  | 234395 |  | 187967 | 7271 | 6519
43 | Wake Forest #2 | 237639 | 2273 | x | 2273 | x |  |  | 7813 | 2273 | 7813 |  |  |  |  | 2983 | 10796 | 15626 |  | 15626 |  | 85235 |  | 85235 |  |  |  | 1966
| Wake Forest #3 |  | 0 | [6 empty] | 0 | [6 empty] | 0
28 | Wake-New Hope #1 | 1040714.0507 | 4829.9653 | x | 4829.9653 |  | 323991.2333 |  | 27133.0405 | 355954.2392 |  |  |  | 20490.4176 |  | 38469.2533 | 58959.6709 | 19888.0925 |  | 19888.0925 |  | 56823.1216 |  | 56823.1216 |  | 0 | 29644.6225 | 27819.1797
31 | Wake-New Hope #2 | 1086955.2864 | 22111.2972 | x | 7813.1792 | x | 14298.118 |  | 9091.6994 | 31202.9966 |  |  |  | 16637.81 |  | 24012.0306 | 40649.8406 | 205093.1132 |  | 205093.1132 |  | 213086.7058 |  | 213086.7058 |  | 72541.8176 | 19132.345 | 15215.8114
32 | Wendell #1 | 238081.7764 | 9233.7573 | x | 2130.8671 | x | 7102.8902 |  | 7244.948 | 16478.7053 |  |  |  | 6386.9189 |  | 11084.7704 | 17471.6893 | 12785.2023 |  | 12785.2023 |  | 65346.5898 | 65346.5898 |  |  | 0 | 7306.0329 | 6611.3702
11 | Wendell #2 | 443802.7851 | 3835.5607 | x | 1278.5202 | x | 2557.0405 |  | 20598.3816 | 24433.9423 |  |  |  | 39466.4991 |  | 1704.6936 | 41171.1927 | 1420.578 | 1420.578 |  |  | 150581.2721 |  | 150581.2721 |  | 0 | 7435.3055 | 1153.5094
19 | Western Wake #1 | 474810 | 0 |  |  |  | 54354 |  | 23013 | 77367 |  |  |  | 1331 |  |  | 1331 | 28412 | 28412 |  |  | 127852 |  | 127852 |  |  | 4147 | 739
29 | Western Wake #2 | 354860 | 0 |  | 3267 |  | 29947 |  | 14014 | 33214 | 14014 | 1705 |  | 41997 |  | 9568 | 67284 | 28412 | 28412 |  |  | 34094 |  | 34094 |  |  | 10457 | 4381
9 | Zebulon #1 | 448880 | 31889 | x | 9518 | x | 22371 |  | 8239 | 40128 |  |  |  | 5689 |  | 10171 | 15860 | 19888 |  | 19888 |  | 127852 |  | 127852 |  |  | 33972 | 7452
|  | 34002716.8987 | 1644324.5805 | 0 | 124788.5318 | 0 | 1281536.282 | 1406324.8138 | 540695.0696 | 1148449.8833 |  | 224736 | 0 | 695901.6456 | 0 | 602970.748 | 2322178.3935 | 4168496.9861 | 2087246.578 | 2081250.4081 | 0 | 3174766.6893 | 1538260.5898 | 1545589.0995 | 0 | 10243042.8176 | 410671.3059 | 1013565.8707
1147498
[10 empty] | 951.8833 | [6 empty] | 3470628.2769 |  |  |  |  | 1587383.5 |  | 3664.2549
3470618
-10.2769
| EMS | [15 empty] | fy 05 | [11 empty] | total ada and protoptype
47 | Apex EMS | 188173 | 37503 | x | 2557 | x | 25286 | x | 9660 |  | x |  |  | 38256 |  | 2990 | 41246 |  |  |  |  | 49436 |  |  |  |  | 15665 | 3077 | 18742 | 188173
| Cary EMS | 252066 | 102589 | x | 1705 | x | 100884 | x | 0 |  | x | 0 |  | 0 | [7 empty] | 82038 |  |  |  |  | 60041 | 7398 | 67439 | 252066
E1 | EMS1 | 0 | 0 | x |  | x |  | x |  |  | x | [17 empty] | 0 | 0
E10 | EMS10 | 81773 | 43327 | x | 71 | x |  | x | 639 |  | x | 42617 |  | 7361 |  | 142 | 7503 |  |  |  |  | 23440 | [6 empty] | 0 | 81773
E15 | EMS15 |  |  | x |  | x |  | x |  |  | x | [17 empty] | 0 | 0
E2 | EMS2 | 126145 | 77941 | x | 1634 | x | 19692 | x | 13998 |  | x | 42617 |  | 7388 |  | 994 | 8382 |  |  |  |  | 23440 |  |  |  |  | 7219 | 781 | 8000 | 126145
E3 | EMS3 | 54903 | 2344 | x | 2344 | x | 0 | x | 0 |  | x | 0 |  | 0 |  | 0 | [5 empty] | 23440 |  |  |  |  | 14207 | 14912 | 29119 | 54903
E4 | EMS4 | 95276 | 56599 | x | 3512 | x | 905 | x | 9565 |  | x | 42617 |  |  |  | 2557 | 2557 |  |  |  |  | 23724 |  |  |  |  | 2455 | 7384 | 9839 | 95276
E5 | EMS5 | 117802 | 74969 | x | 2273 | x | 1236 | x | 28843 |  | x | 42617 |  | 7602 |  | 426 | 8028 |  |  |  |  | 23866 |  |  |  |  | 980 | 1931 | 2911 | 117802
E6 | EMS6 | 0 | 0 | x |  | x |  | x |  |  | x | [17 empty] | 0 | 0
E7 | EMS7 | 86540 | 48229 | x | 1634 | x |  | x | 3978 |  | x | 42617 |  | 7116 |  |  | 7116 |  |  |  |  | 24008 |  |  |  |  | 71 |  | 71 | 86540
E8 | EMS8 | 71785 | 43966 | x |  | x | 355 | x | 994 |  | x | 42617 |  | 723 |  | 426 | 1149 |  |  |  |  | 23440 | [5 empty] | 2081 | 2081 | 71785
87 | Garner EMS | 270064 | 38789 | x | 1705 | x | 37084 |  | 21753 |  | x |  |  | 38331 |  | 426 | 60510 |  |  |  |  | 93758 |  |  |  |  | 4806 | 11691 | 16497 | 270064
87 | Holly Springs EMS | 7137 | 0 | x | 0 | x | 0 |  | 0 |  | x | 0 |  | 0 |  | 0 | [5 empty] | 0 |  |  |  |  | 3321 | 3816 | 7137 | 7137
137 | Knightdale EMS | 227632 | 45353 | x | 22455 | x | 7840 | x | 14206 |  | x | 852 |  | 38434 |  | 7863 | 46297 |  |  |  |  | 70319 |  |  |  |  | 3215 | 16151 | 19366 | 227632
157 | Rolesville EMS | 0 | 0 | x |  | x |  |  |  |  | x | [17 empty] | 0 | 0
127 | Six Forks Rescue | 460151 | 37543 | x | 852 | x | 34986 |  | 7245 |  | x | 1705 |  | 79726 |  | 38782 | 125753 | 0 |  |  |  | 90917 |  |  |  |  | 46621 | 33564 | 80185 | 460151
117 | Wendell EMS | 150873 | 32261 | x | 284 | x | 31977 |  | 15484 |  | x |  |  | 16489 |  | 1321 | 33294 |  |  |  |  | 35159 |  |  |  |  | 7212 | 9653 | 16865 | 150873
97 | Zebulon EMS | 149267 | 84863 | x | 1634 | x | 83229 |  | 0 |  | x | 0 |  | 0 |  | 0 | [5 empty] | 35159 |  |  |  |  | 27194 | 2051 | 29245 | 149267
|  |  | 726276 |  | 42660 |  | 343474 |  | 126365 |  |  | 258259 |  | 241426 |  | 55927 | 341835 | [9 empty] | 193007 | 114490 | 307497
307497
|  | FY 04 total for 1 - 6 | 726276
|  | FY 05 total for 1 - 6 | 341835
|  | total for 1-6 | 1068111
1068111