Wake County Fire Commission

Facility Committee

MEMO TO:	Fire Commission Members

FROM:	Ed Brinson, Chairman

DATE:	September 23, 2010

SUBJECT:	Facility Committee Report

The Facility Committee met on August 27 and September 15, 2010 at Garner Fire Station No. 1 and we respectfully offer the following report:

Status of the Garner Fire Station No.  4 Project

- The project is on schedule for completion in October with a projected move in during November 2010.

- Mark Forestieri reported that the project costs are on target.

Bayleaf Headquarters Fire Station Reconstruction Project

- Chief Roof reported that the fire department and the county had come to terms on the lease and ownership agreement.  There are two addendums outstanding and they concern a release of liability and continued facility maintenance.

Status of the Bay Leaf Station No. 3, Hopkins and Durham Highway Renovation Projects

- Bay Leaf has the funding agreement from the county and they are in the process of planning and bidding the projects.

- Hopkins has executed the funding agreement and the bids.  The project has started.

- Durham-Highway has submitted the funding agreement and has completed their project.

Zebulon Fire Station No. 2 Construction Project

- Chief Perry submitted a CIP request to the facility committee to determine if there was an opportunity for the county to partially fund a second Zebulon fire station.  The western side of town is the proposed location for the new fire station.

- The facility committee agreed to review data and costs related to the fire station project.

- The facility committee will discuss this project at the next meeting.

- A recommendation will be forthcoming from the facility committee regarding this project.

- No action by the Fire Commission is required at this time.

Wendell Falls Fire Station Project

Facilities, Design and Construction are in negotiation to purchase the property for the Fire/EMS station.

Fire Station Dormitory Renovation Project

- Patrick McHugh, the Project Manager from Wake County Facilities Design and Construction reported that all of the fire stations that received renovations or additions are substantially complete.

- All renovated spaces are occupied.

- A few punch list items are left to complete.

- Patrick reports that all costs are within the original estimates.  It should be noted that a few invoices have not been paid.  The following are the total cost incurred to date.

Soft Costs

Pre-Design/Study 	$93,281.00

Design Services 	$605,840.00

Land Surveys 	$65,425.00

Subsurface Investigations 	$13,294.00

Construction Material Testing 	$25,911.00

Roofing Consultant 	$4,575.00

Plan Review Fees 	$763.00

Soft Cost Total: 	$809,089.00

|  | Bayleaf 36-2 | Fairview 20-1 | Fairview 34-2 | Stony Hill 39-2 | Swift Creek 27 |
| --- | --- | --- | --- | --- | --- |
| Base Construction Contract | $ 306,984.00 | $ 437,898.00 | $ 532,606.00 | $ 508,212.00 | $ 253,430.00 |
| Change Order Cost | $ 27,403.00 | $ 69,490.87 | $ 68,041.35 | $ 32,313.88 | $ 142,061.90 |
| Total Construction Costs | $ 334,387.00 | $ 507,388.87 | $ 600,647.35 | $ 540,525.88 | $ 395,491.90 |
| Surveying (All) | $12,550.00 |
| Utilities (All) | $8,262.00 |
| Furnishings, Fixtures & Equip. |  |  |  |  |  |
| Nightstands | $ 1,857.99 | $ 1,206.90 | $ 1,206.90 | $ 1,206.90 | $ - |
| Mattress/Box springs | $ 1,688.42 | $ 1,125.60 | $ 1,125.60 | $ 1,125.60 | $ - |
| Telephone Systems (All) | $4,385.00 |
| Total FF&E, Utility and Survey Cost | $34,741.00 |
| Total Project Cost | $3,223,271.00 |